## Wx
PROJECT REPORT
Group | 5
Week | 07/09/2022-17/09/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS Document & Web Skeleton | In Progress | Overall contents as listed in the part I of the SRS document, Web Skeleton
2 | Design Document | In Progress | Overall contents as listed in the part I of the Design Document
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Contents of the SRS .Document | Võ Chí Cường | Listed in the part I
2 | Web Skeleton | Huỳnh Chí Cường | HTML, CSS, JS files
3 | The system functions | Phan Thiên Ân | Listed in the part II
4 | Overall content of the Design Document | Quang Minh, Quang Quý | Workable codes, acted as the code skeleton for the team to follow during the coding phase
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Web Skeleton is not available | In Progress
| The group met with incomplete HTML and CSS | In Progress
| Having difficulty in new and unfixed functions | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Prepare code designs | Pending | packages, classes, attributes and methods
2 | Review and evaluate the team's design |  | web skeleton, code
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
| Difficulty when coding Front-end and back-end | In Progress | HTML,CSS
| There is a new function that is still in testing | In Progress | Many bugs in the program, progress is a bit slow
| Database is not yet standard | In Progress | Undetermined yet
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C18: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue