## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
Function Register | Feature 1 | Simple | Iteration 2 | SE150679 | Huỳnh Chí Cường | Iteration 3
Function Log in | Feature 1 | Simple | Iteration 1 | SE150623 | Phan Thiên Ân | Iteration 3
Function Remember Password | Feature 1 | Medium | Iteration 2 | SE150674 | Võ Chí Cường | Iteration 3
Function Forgot Password | Feature 1 | Medium | Iteration 3 | SE140461 | Nguyễn Quang Minh | Iteration 3
Function Encode Password | Feature 1 | Medium | Iteration 2 | SE63160 | Phạm Quang Quý | Iteration 3
Function Add Product | Feature 2 | Medium | Iteration 2 | SE150623 | Phan Thiên Ân | Iteration 3
Function Remove Product | Feature 2 | Simple | Iteration 2 | SE150623 | Phan Thiên Ân | Iteration 3
Function Update Product | Feature 2 | Medium | Iteration 2 | SE150623 | Phan Thiên Ân | Iteration 3
Function Logout | Feature 1 | Simple | Iteration 1 | SE150679 | Huỳnh Chí Cường | Iteration 3
Function Change Password | Feature 1 | Simple | Iteration 1 | SE150679 | Huỳnh Chí Cường | Iteration 3
Function Dashboard | Feature 3 | Complex | Iteration 3 | SE150674 | Võ Chí Cường | Iteration 3
Function View Product | Feature 2 | Medium | Iteration 2 | SE63160 | Phạm Quang Quý | Iteration 3
Function Get Feedback | Feature 3 | Complex | Iteration 3 | SE140461 | Nguyễn Quang Minh | Iteration 3
Function Add New Product | Feature 3 | Medium | Iteration 2 | SE140461 | Nguyễn Quang Minh | Iteration 3