## W1
PROJECT REPORT
Group | 5
Week | 07/09/2022-17/09/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS Document & Web Skeleton | In Progress | Overall contents as listed in the part I of the SRS document, Web Skeleton
2 | Design Document | In Progress | Overall contents as listed in the part I of the Design Document
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Contents of the SRS .Document | Võ Chí Cường | Listed in the part I
2 | Web Skeleton | Huỳnh Chí Cường | HTML, CSS, JS files
3 | The system functions | Võ Chí Cường | Listed in the part II
4 | Overall content of the Design Document | Quang Minh | Workable codes, acted as the code skeleton for the team to follow during the coding phase
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Web Skeleton is not available | In Progress
| The group met with incomplete HTML and CSS | In Progress
| Having difficulty in new and unfixed functions | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Prepare code designs | Pending | packages, classes, attributes and methods
2 | Review and evaluate the team's design |  | web skeleton, code
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
| Difficulty when coding Front-end and back-end | In Progress | HTML,CSS
| There is a new function that is still in testing | In Progress | Many bugs in the program, progress is a bit slow
| Database is not yet standard | In Progress | Undetermined yet
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C18: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W2
PROJECT REPORT
Group | 5
Week | 18/09/2022-1/10/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS Document & Web Skeleton | Completed | Overall contents as listed in the part 2 of the SRS document, Web Skeleton
2 | Design Document | Completed | Overall contents as listed in the part 2 of the Design Document
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Learn how to pay by PayPal | Võ Chí Cường | used sandbox PayPal
2 | Login, Register, Change Pass | Huỳnh Chí Cường | bind false errors
3 | Fix and Edit HTML | Phan Thiên Ân | Learn more boostrap and html,css,js to make app beauty
4 | CRUD product and Shopping feature | Huỳnh Chí Cường | Stabilize and finish it all
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Combine new function and new database | In Progress
| The group met with incomplete HTML and CSS | In Progress
| Having difficulty in new and unfixed functions | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Prepare code designs | Pending | packages, classes, attributes and methods
2 | Review and evaluate the team's design |  | web skeleton, code
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
| Difficulty when coding Front-end and back-end | In Progress | HTML,CSS
| There is a new function that is still in testing | In Progress | Many bugs in the program, progress is a bit slow
| Database is not yet standard | In Progress | Undetermined yet
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C18: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W3
PROJECT REPORT
Group | 5
Week | 2/09/2022-16/10/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS Document & Web Skeleton | Completed | Overall contents as listed in the part 2 of the SRS document, Web Skeleton
2 | Design Document | Completed | Overall contents as listed in the part 2 of the Design Document
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Comment | Võ Chí Cường | display comment of user
2 | Conntact | Huỳnh Chí Cường | get contact
3 | Render data | Quang Minh | load data on page
4 | front-end | Quang Minh | fix front suitable
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Not complete | In Progress
| Have problem about code | In Progress
| Not enough functions | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
Complete all function |  | Pending
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C18: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W4
PROJECT REPORT
Group | 5
Week | 17/10/2022-31/10/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS Document & Web Skeleton | Completed
2 | Design Document | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Implement the Job Posting function | Võ Chí Cường
2 | Implement the Job Posting function | Huỳnh Chí Cường
3 | Implement the Job Posting function | Quang Minh
4 | Project status,shopping cart,checkout | Huỳnh Chí Cường
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Unable to view cart details function | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Prepare to present and design website | Pending
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
| Format and design template | In Progress
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C18: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue