## Assignemnts-original
THE APPLICATION DEVELOPMENT PROJECT TOPIC
STUDENT ASSIGNMENTS
Detailed Student LOC Evaluation
Function Name | Assignment Name | Function Complexity |  | Planned Code Iteration | Roll Number | Full Name | Team | Actual Code Iteration | Iteration Code Quality | Iteration Source Code Comments | Iteration LOC | Final Code Quality | Final Source Code Comments | Final LOC
Function Login | GameStore | Simple | 60 | Iteration 1 | SE150679 | Huỳnh Chí Cường | T5 | Iteration 1 | High |  | 60 | Medium |  | 90
Function PaybyPaypal | GameStore | Medium | 120 | Iteration 2 | SE150623 | Phan Thiên Ân | T5 | Iteration 2 | Low |  | 60 | Low |  | 120
Function Filter | GameStore | Complex | 240 | Iteration 3 | SE150674 | Võ Chí Cường | T5 | Iteration 3 | Medium |  | 180 | Low |  | 60
Function BuyProduct | GameStore | Medium | 120 | Iteration 1 | SE140461 | Nguyễn Quang Minh | T5 | Iteration 1 | Medium |  | 90 | Medium |  | 180
Function AddPoduct | GameStore | Complex | 240 | Iteration 2 | SE63160 | Phạm Quang Quý | T5 | Iteration 2 | Medium |  | 180 | Medium |  | 180
Function Register | GameStore | Complex | 240 | Iteration 2 | SE05407 | Nguyễn Mạnh Hiếu | T5 | Iteration 3 | High |  | 240 | High |  | 60
Function Search | GameStore | Simple | 60 | Iteration 1 | SE140461 | Nguyễn Quang Minh | T5 | Iteration 1 | Medium |  | 45 | Medium |  | 45
Function ResetPass | GameStore | Simple | 60 | Iteration 1 | SE150679 | Huỳnh Chí Cường | T5 | Iteration 1 | Medium |  | 45 | Medium
Function ForgotPass | GameStore | Simple | 60 | Iteration 1 | SE150674 | Võ Chí Cường | T5 | Iteration 1 | Medium |  | 45 | Medium

## Assignemnts-original (2)
THE APPLICATION DEVELOPMENT PROJECT TOPIC
STUDENT ASSIGNMENTS
Detailed Student LOC Evaluation
Function Name | Assignment Name | Function Complexity | Function LOC | Planned Code Iteration | Roll Number | Full Name | Team | Actual Code Iteration | Iteration Code Quality | Iteration Source Code Comments | Iteration LOC | Final Code Quality | Final Source Code Comments | Final LOC
Function Name 1 | Asssignment Name 1 | Simple | 60 | Iteration 1 | SE05407 | Nguyễn Mạnh Hiếu | T1 | Iteration 1 | High |  | 60 | Medium |  | 90
Function Name 2 | Asssignment Name 1 | Medium | 120 | Iteration 2 | SE05436 | Đinh Trọng Tuấn | T2 | Iteration 2 | Low |  | 60 | Low |  | 120
Function Name 3 | Asssignment Name 1 | Complex | 240 | Iteration 3 | SE04964 | Phạm Thanh Tùng | T2 | Iteration 3 | Medium |  | 180 | Low |  | 60
Function Name X | Asssignment Name 2 | Medium | 120 | Iteration 1 | SE05725 | Phan Duy Thịnh | T3 | Iteration 1 | Medium |  | 90 | Medium |  | 180
Function Name Y | Asssignment Name 2 | Complex | 240 | Iteration 2 | SE05407 | Nguyễn Mạnh Hiếu | T1 | Iteration 2 | Medium |  | 180 | Medium |  | 180
Function Name Z | Asssignment Name 2 | Complex | 240 | Iteration 2 | SE05407 | Nguyễn Mạnh Hiếu | T1 | Iteration 3 | High |  | 240 | High |  | 60
-- | -- | Simple | 60 | Iteration 1 | -- | -- |  | Iteration 1 | Medium |  | 45 | Medium |  | 0

## Iteration-LOC
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ACTUAL ITERATION LOC FOR EACH STUDENT
| Sum of Iteration LOC | Column Labels
Student Name | Row Labels | Iteration 1 | Iteration 2 | Iteration 3 | Grand Total
#N/A | -- | 45 |  |  | 45
#N/A | SE04964 |  |  | 135 | 135
Nguyễn Mạnh Hiếu | SE05407 | 60 | 135 | 180 | 375
#N/A | SE05436 |  | 60 |  | 60
#N/A | SE05725 | 90 |  |  | 90
| Grand Total | 195 | 195 | 315 | 705

## Final-LOC
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ACTUAL FINAL LOC FOR EACH STUDENT
Student Name | Row Labels | Sum of Final LOC
#N/A | -- | 45
#N/A | SE04964 | 135
Nguyễn Mạnh Hiếu | SE05407 | 360
#N/A | SE05436 | 90
#N/A | SE05725 | 90
| Grand Total | 720